## Sheet1
Task # | Task Name | Duration | Start Date | Finish Date | Dependency | Resource | Outline Level | % Complete | Task Notes | Actual Start | Actual Finish | Actual Duration | User Defined Number | User Defined Time | User Defined Text 1 | User Defined Text 2 | User Defined Text 3 | User Defined Text 4 | User Defined Text 5 | User Defined Decimal | User Defined Duration
1 | Meeting with Baylee (Problem) | 2 | 2020-01-13 08:00 | 2020-01-14 16:00 |  | Team | 1 | 0 |  | 2020-01-13 08:00 |  |  | 0 | 2014-05-12 10:40 | [5 empty] | 0 | 1
2 | Document Current System | 1 | 2020-01-15 08:00 | 2020-01-15 16:00 | 1 | Business Analyst | 1 | 0 |  | 2020-01-15 08:00 |  |  | 0 | 2014-05-16 10:40 | [5 empty] | 0 | 1
3 | Research Similar Websites | 3 | 2020-01-16 08:00 | 2020-01-20 16:00 | 2 | Business Analyst | 1 | 0 |  | 2020-01-16 08:00 |  |  | 0 | 2014-05-21 10:40 | [5 empty] | 0 | 1
4 | Discussions with Project Manager | 1 | 2020-01-21 08:00 | 2020-01-21 16:00 | 3 | Business Analyst | 1 | 0 |  | 2020-01-21 08:00 |  |  | 0 | 2014-05-22 10:40 | [5 empty] | 0 | 1
5 | Financial Analysis (NPV) | 3 | 2020-01-22 08:00 | 2020-01-24 16:00 |  | Business Analyst | 1 | 0 |  | 2020-01-22 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
6 | Design Interface Brainstorm | 1 | 2020-01-24 08:00 | 2020-01-24 16:00 |  | Web Developer | 1 | 0 |  | 2020-01-24 08:00 |  |  | 0 | 2014-05-29 10:40 | [5 empty] | 0 | 1
7 | Iteration 1: System Request Presentation | 1 | 2020-01-27 08:00 | 2020-01-27 16:00 |  | Team | 1 | 0 |  | 2020-01-27 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
8 | Meeting with Baylee (Requirements) | 1 | 2020-01-31 08:00 | 2020-01-31 16:00 |  | Business Analyst | 1 | 0 |  | 2020-01-31 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
9 | List Requirements | 1 | 2020-01-31 08:00 | 2020-01-31 16:00 |  | Project Manager | 1 | 0 |  | 2020-01-31 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
10 | Discuss considerations and risk analysis | 1 | 2020-02-03 08:00 | 2020-02-03 16:00 | 9 | Business Analyst | 1 | 0 |  | 2020-02-03 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
11 | Create prototypes | 6 | 2020-02-04 08:00 | 2020-02-11 16:00 |  | Web Developer | 1 | 0 |  | 2020-02-04 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
12 | Add on to design interface | 4 | 2020-02-12 08:00 | 2020-02-17 16:00 |  | Web Developer | 1 | 0 |  | 2020-02-12 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
13 | Iteration 2: Inception Phase Presentation | 1 | 2020-02-18 08:00 | 2020-02-18 16:00 |  | Team | 1 | 0 |  | 2020-02-18 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
14 | Used Cases | 1 | 2020-02-19 08:00 | 2020-02-19 16:00 |  | Business Analyst | 1 | 0 |  | 2020-02-19 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
15 | Develop Modules | 2 | 2020-02-20 08:00 | 2020-02-21 16:00 |  | Web Developer | 1 | 0 |  | 2020-02-20 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
16 | Add on to prototypes | 6 | 2020-02-24 08:00 | 2020-03-02 16:00 |  | Web Developer | 1 | 0 |  | 2020-02-24 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
17 | Integrate Database | 9 | 2020-03-03 08:00 | 2020-03-13 16:00 | 16 | Database Developer | 1 | 0 |  | 2020-03-03 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
18 | Plan unit tests | 2 | 2020-03-13 08:00 | 2020-03-16 16:00 |  | Project Manager | 1 | 0 |  | 2020-03-13 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
19 | Iteration 3: Use Case, Prototype | 1 | 2020-03-16 08:00 | 2020-03-16 16:00 |  | Team | 1 | 0 |  | 2020-03-16 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
20 | Add on to Use Cases | 2 | 2020-03-17 08:00 | 2020-03-18 16:00 |  | Business Analyst | 1 | 0 |  | 2020-03-17 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
21 | Add on to prototypes | 9 | 2020-03-17 08:00 | 2020-03-27 16:00 |  | Development Team | 1 | 0 |  | 2020-03-17 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
22 | Iteration 4: Use case, Prototype v2 | 1 | 2020-03-30 08:00 | 2020-03-30 16:00 |  | Team | 1 | 0 |  | 2020-03-30 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
23 | Develop User Interface | 4 | 2020-03-31 08:00 | 2020-04-03 16:00 | 22 | Web Developer | 1 | 0 |  | 2020-03-31 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
24 | Test Interface | 1 | 2020-04-03 08:00 | 2020-04-03 16:00 |  | Project Manager | 1 | 0 |  | 2020-04-03 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
25 | Add security protocols | 1 | 2020-04-03 08:00 | 2020-04-03 16:00 |  | Database Developer | 1 | 0 |  | 2020-04-03 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
26 | Perform system tests | 1 | 2020-04-06 08:00 | 2020-04-06 16:00 |  | Project Manager | 1 | 0 |  | 2020-04-06 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
27 | Document problems | 1 | 2020-04-06 08:00 | 2020-04-06 16:00 |  | Development Team | 1 | 0 |  | 2020-04-06 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
28 | Iteration 5: User Interface, Prototype | 1 | 2020-04-08 08:00 | 2020-04-08 16:00 |  | Team | 1 | 0 |  | 2020-04-08 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
29 | Implement payment system | 4 | 2020-04-09 08:00 | 2020-04-14 16:00 |  | Web Developer | 1 | 0 |  | 2020-04-09 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
30 | Implement fixes | 1 | 2020-04-14 08:00 | 2020-04-14 16:00 |  | Development Team | 1 | 0 |  | 2020-04-14 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
31 | Iteration 6: Elaboration Phase | 1 | 2020-04-15 08:00 | 2020-04-15 16:00 |  | Team | 1 | 0 |  | 2020-04-15 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
32 | System Checks | 3 | 2020-04-16 08:00 | 2020-04-20 16:00 |  | Project Manager | 1 | 0 |  | 2020-04-16 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
33 | Implement fixes | 3 | 2020-04-20 08:00 | 2020-04-22 16:00 |  | Development Team | 1 | 0 |  | 2020-04-20 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1
34 | Meeting with Baylee | 1 | 2020-04-24 08:00 | 2020-04-24 16:00 |  | Business Analyst | 1 | 0 |  | 2020-04-24 08:00 |  |  | 0 | 2020-01-13 10:40 | [5 empty] | 0 | 1